## Dashboard
AI Engineering Lab, 24-Week AI Engineering Program
Find the Signal. Act with Intelligence. · by Zorost Intelligence (https://zorost.com)
| Learner name | Marko | Start date | 15.Sept.2026
| Program start |  | Target end (24 weeks later)
Week | Section | Title | Status | % Complete
Week 01 | Foundations | Python Foundations & the AI Engineering Landscape | ▶ In progress | 14.29%
Week 02 | Foundations | Data Engineering & SQL for AI | ☐ Not started | 0%
Week 03 | Foundations | Machine Learning Fundamentals | ☐ Not started | 0%
Week 04 | Foundations | Deep Learning with PyTorch | ☐ Not started | 0%
Week 05 | LLM Core | How LLMs Work: Tokens to Transformers | ☐ Not started | 0%
Week 06 | LLM Core | Prompt Engineering & the Context Window | ☐ Not started | 0%
Week 07 | LLM Core | RAG, Vector Search & Knowledge Graphs | ☐ Not started | 0%
Week 08 | LLM Core | Open Models & Local Inference: GPUs, Ollama, llama.cpp | ☐ Not started | 0%
Week 09 | Model Engineering | Quantization & Efficient Inference | ☐ Not started | 0%
Week 10 | Model Engineering | Fine-Tuning: LoRA, SFT & DPO | ☐ Not started | 0%
Week 11 | Model Engineering | Evals & Error Analysis for AI Systems | ☐ Not started | 0%
Week 12 | Harnesses & Loops | Coding-Agent Harnesses: Claude Code, Cursor, OpenCode, DSH | ☐ Not started | 0%
Week 13 | Harnesses & Loops | Agentic Coding Loops & Spec-Driven Development | ☐ Not started | 0%
Week 14 | Agents | Agent Fundamentals: The Loop, Tools & Memory | ☐ Not started | 0%
Week 15 | Agents | Agent Frameworks: LangGraph & the State-Graph Model | ☐ Not started | 0%
Week 16 | Agents | Multi-Agent Systems & MCP | ☐ Not started | 0%
Week 17 | Agents | OpenClaw, Hermes & Agent Operations | ☐ Not started | 0%
Week 18 | Cloud AI Platforms | Azure AI Foundry | ☐ Not started | 0%
Week 19 | Cloud AI Platforms | Google Vertex AI & Gemini | ☐ Not started | 0%
Week 20 | Cloud AI Platforms | AWS Bedrock & SageMaker AI | ☐ Not started | 0%
Week 21 | Databricks Zero to Hero | Databricks Day Zero: Unity Catalog & the Lakehouse | ☐ Not started | 0%
Week 22 | Databricks Zero to Hero | Databricks Data Engineering: PySpark, Streaming & Lakeflow | ☐ Not started | 0%
Week 23 | Databricks Zero to Hero | Databricks ML & GenAI: Training, Serving, Genie | ☐ Not started | 0%
Week 24 | Databricks Zero to Hero | Databricks Production: DABs, Governance & the Capstone | ☐ Not started | 0%
|  |  | Overall completion | 0.5952%
Phase summary
Foundations | Weeks 1 to 4 | 3.571% | Python, data engineering, classical ML, and deep learning, taught the AI engineering way: every model ships with a metric, a split, and an error analysis.
LLM Core | Weeks 5 to 8 | 0% | How LLMs actually work, from tokens and embeddings to attention and the KV cache, then the two engineering superpowers on top: prompt & context-window engineering, and retrieval (RAG + knowledge graphs). Week 8 goes fully local.
Model Engineering | Weeks 9 to 11 | 0% | Make models cheaper and yours: quantization formats and serving engines, fine-tuning with LoRA/SFT/DPO, and the discipline that decides it all, evals and error analysis.
Harnesses & Loops | Weeks 12 to 13 | 0% | Become dangerous with coding agents: Claude Code, Cursor, OpenCode, DeepSeek Harness, then run the three loops (agentic coding → developer feedback → external feedback) with a spec, a verifier, and a blast-radius rule.
Agents | Weeks 14 to 17 | 0% | From a hand-written ReAct loop to LangGraph state graphs, multi-agent orchestration, and MCP, then OpenClaw as a personal assistant and agent operations.
Cloud AI Platforms | Weeks 18 to 20 | 0% | The same ZoroLogistics support agent, deployed three ways: Azure AI Foundry (Microsoft), Vertex AI + AI Studio (Google), Bedrock + SageMaker (AWS). Compare capabilities, governance, and cost, then learn how to pick.
Databricks Zero to Hero | Weeks 21 to 24 | 0% | The full Zorost Databricks modernization playbook: Unity Catalog, Delta Lake medallion, DBSQL, PySpark, streaming, Lakeflow, MLflow, Mosaic AI, Genie, then DABs, CI/CD, governance, and FinOps, ending in the lakehouse capstone.
Legend
☐ Not started | not started yet
▶ In progress | working on it
✅ Done | completed, pick this to tick it off ✅
⏭ Skipped | skipped deliberately (explain in Notes)

## Week 01
Week 01, Python Foundations & the AI Engineering Landscape
Section: Foundations · Category: Python & Environment · ZoroLogistics case study
🎯 Use case: Generate the ZoroLogistics synthetic dataset (shipments, carriers, lanes) that every future week reuses.
Day | Task | Status | Notes
Mon | Set up VS Code, Python environment (uv or conda), and git; fork/clone the repo. | ✅ Done | 6
Tue | Complete the Python refresher exercises in the environment notebook. | ☐ Not started
Wed | Run the environment check notebook end-to-end (versions, imports, deterministic seed). | ☐ Not started
Thu | Build the ZoroLogistics data generator: shipments, carriers, lanes, deterministic seeds. | ☐ Not started
Fri | Use case: generate the 100k-row dataset, save to CSV/Parquet, commit it with a data dictionary. | ☐ Not started
Sat | Take the Week 1 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker: Week 1 checked off; push your fork to GitHub. | ☐ Not started
Week completion | 14.29% | ███░░░░░░░░░░░░░░░░░ |  | Deliverables: Working local environment (checklist notebook passes) · ZoroLogistics data generator (100k rows, seeded) · Data dictionary for the generated dataset

## Week 02
Week 02, Data Engineering & SQL for AI
Section: Foundations · Category: Data & SQL · ZoroLogistics case study
🎯 Use case: Clean and profile the raw shipment dataset into an analytics-ready 'silver' table.
Day | Task | Status | Notes
Mon | Study data quality concepts; run the pandas refresher exercises. | ☐ Not started
Tue | Run the pandas cleaning notebook; find and document 5 data issues in the generator output. | ☐ Not started
Wed | Write SQL queries in DuckDB: on-time rate by carrier/lane/month, windows, top-lane analysis. | ☐ Not started
Thu | Add a data validation suite (pandera) with at least 10 checks. | ☐ Not started
Fri | Use case: deliver the cleaned silver dataset + profile report; document every cleaning decision. | ☐ Not started
Sat | Take the Week 2 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the silver pipeline script. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Silver dataset + validation suite (10+ checks) · SQL analytics queries (on-time rate by carrier/lane/month) · Data profile report

## Week 03
Week 03, Machine Learning Fundamentals
Section: Foundations · Category: Classical ML · ZoroLogistics case study
🎯 Use case: Baseline ETA (estimated time of arrival) regression and on-time classification from shipment features.
Day | Task | Status | Notes
Mon | Study supervised learning and the eval mindset: pick the metric before the model. | ☐ Not started
Tue | Run the ETA regression baseline; log MAE/RMSE for 3 models in a comparison table. | ☐ Not started
Wed | Implement a time-aware split and cross-validation; compare models fairly. | ☐ Not started
Thu | On-time classification: precision/recall/F1, threshold tradeoff, confusion matrix. | ☐ Not started
Fri | Use case: write the Week 3 model card (metric, split, top error source) and commit it. | ☐ Not started
Sat | Take the Week 3 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; log all experiments to a JSON experiment log. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: ETA regression baseline with logged metrics · On-time classifier with threshold tradeoff analysis · Week 3 model card (metric, split, top error source)

## Week 04
Week 04, Deep Learning with PyTorch
Section: Foundations · Category: Deep Learning · ZoroLogistics case study
🎯 Use case: A neural ETA model that beats the Week 3 baseline, with a first error analysis by carrier and lane.
Day | Task | Status | Notes
Mon | Study tensors, autograd, and the computation-graph mental model. | ☐ Not started
Tue | Run the MLP notebook; verify loss curves; deliberately break one thing and diagnose it. | ☐ Not started
Wed | Add dropout/weight decay; tune 3 hyperparameters using the validation split. | ☐ Not started
Thu | Compare neural vs baseline on the test set; segment errors by carrier and lane. | ☐ Not started
Fri | Use case: write the error-analysis note (biggest error cluster + hypothesis). | ☐ Not started
Sat | Take the Week 4 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit model card v2. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: PyTorch MLP training notebook with learning curves · Neural vs baseline comparison on the test set · Error analysis note: biggest error cluster + hypothesis

## Week 05
Week 05, How LLMs Work: Tokens to Transformers
Section: LLM Core · Category: LLM Internals · ZoroLogistics case study
🎯 Use case: Shipment-note token cost estimator plus embedding similarity search over commodity descriptions.
Day | Task | Status | Notes
Mon | Study tokenization and embeddings (knowledge-base 03). | ☐ Not started
Tue | Tokenizer lab: BPE encode/decode and a token-cost estimator for the LLM API. | ☐ Not started
Wed | Embeddings lab: similarity search over shipment commodity descriptions. | ☐ Not started
Thu | Attention lab: implement scaled dot-product attention in NumPy; visualize the weights. | ☐ Not started
Fri | Use case: build the context-window budget calculator (tokens per call vs window size). | ☐ Not started
Sat | Take the Week 5 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit both labs. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Tokenizer lab with cost estimator · Embedding similarity search over commodities · Context-window budget calculator

## Week 06
Week 06, Prompt Engineering & the Context Window
Section: LLM Core · Category: Prompt & Context · ZoroLogistics case study
🎯 Use case: Extract bill-of-lading fields reliably with a prompt suite and per-field accuracy eval.
Day | Task | Status | Notes
Mon | Study prompt engineering and context engineering (knowledge-base 04). | ☐ Not started
Tue | Build the BoL extraction prompt suite; run it against 20 synthetic documents. | ☐ Not started
Wed | Add structured outputs and few-shot examples; improve per-field accuracy. | ☐ Not started
Thu | Context engineering: budgets, compaction, caching. Measure tokens and latency. | ☐ Not started
Fri | Use case: reach 90%+ field accuracy on the eval set; document the failure cases. | ☐ Not started
Sat | Take the Week 6 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the prompt suite and eval results. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: BoL extraction prompt suite + eval results · Structured-output pipeline · Context engineering measurements (tokens, latency, cache hits)

## Week 07
Week 07, RAG, Vector Search & Knowledge Graphs
Section: LLM Core · Category: Retrieval & Graphs · ZoroLogistics case study
🎯 Use case: A shipping-policy Q&A bot (RAG with citations) plus a carrier-lane-port knowledge graph.
Day | Task | Status | Notes
Mon | Study retrieval fundamentals (knowledge-base 05). | ☐ Not started
Tue | Chunk and embed the policy corpus; build a vector index; measure baseline retrieval accuracy. | ☐ Not started
Wed | Add hybrid search and reranking; cite sources in answers; measure groundedness. | ☐ Not started
Thu | Build the carrier-lane-port graph in Neo4j; query shortest and cheapest routes. | ☐ Not started
Fri | Use case: the RAG bot answers 10 unseen questions with citations; log retrieval misses. | ☐ Not started
Sat | Take the Week 7 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit RAG and graph labs. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: RAG policy bot with citations · Retrieval accuracy and groundedness measurements · Carrier-lane-port graph with route queries

## Week 08
Week 08, Open Models & Local Inference: GPUs, Ollama, llama.cpp
Section: LLM Core · Category: Local Models & GPUs · ZoroLogistics case study
🎯 Use case: Run a local model to triage support tickets offline, plus a VRAM sizing calculator for model choice.
Day | Task | Status | Notes
Mon | Study the model landscape: open vs closed, licenses, families (knowledge-base 08). | ☐ Not started
Tue | Install Ollama; pull a small model; run chat and structured outputs locally. | ☐ Not started
Wed | Try llama.cpp and MLX; compare tokens/sec across backends in a table. | ☐ Not started
Thu | GPU setup check: CUDA/MPS/ROCm; benchmark with a small script. | ☐ Not started
Fri | Use case: ticket triage with a local model + the VRAM-based model picker. | ☐ Not started
Sat | Take the Week 8 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the benchmark table and picker. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Local model playground notebook · Backend benchmark table (tokens/sec) · VRAM-based model picker

## Week 09
Week 09, Quantization & Efficient Inference
Section: Model Engineering · Category: Quantization & Serving · ZoroLogistics case study
🎯 Use case: Quantize the triage model, serve it with vLLM, and publish a quality-vs-speed report.
Day | Task | Status | Notes
Mon | Study numeric formats and quantization methods (knowledge-base 06). | ☐ Not started
Tue | Quantize a 7B or 8B model with bitsandbytes; measure quality on the triage eval. | ☐ Not started
Wed | GGUF sweep with llama.cpp: Q4/Q5/Q8; record perplexity and speed. | ☐ Not started
Thu | Serve with vLLM (OpenAI-compatible API); benchmark latency and throughput. | ☐ Not started
Fri | Use case: publish the quality-vs-cost report; pick the production quantization. | ☐ Not started
Sat | Take the Week 9 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the report. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Quantization sweep with quality measurements · vLLM serving + benchmark notebook · Quality-vs-cost report with a production recommendation

## Week 10
Week 10, Fine-Tuning: LoRA, SFT & DPO
Section: Model Engineering · Category: Fine-tuning · ZoroLogistics case study
🎯 Use case: Fine-tune a small open model on ZoroLogistics support tone and bill-of-lading entity extraction.
Day | Task | Status | Notes
Mon | Study fine-tuning theory and the selection order (knowledge-base 06). | ☐ Not started
Tue | Build the SFT dataset (instructions + responses) from the Week 6 corpus. | ☐ Not started
Wed | Train LoRA with TRL/Unsloth (Colab free tier or local GPU); log loss curves. | ☐ Not started
Thu | Create preference pairs; run a small DPO step; compare before/after on the eval. | ☐ Not started
Fri | Use case: publish the before/after eval table; decide deploy vs iterate. | ☐ Not started
Sat | Take the Week 10 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the adapter and eval results. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: SFT dataset built from the Week 6 corpus · LoRA adapter + training logs · Before/after eval table and a deploy/no-deploy decision

## Week 11
Week 11, Evals & Error Analysis for AI Systems
Section: Model Engineering · Category: Evaluation · ZoroLogistics case study
🎯 Use case: Build ZoroEval, the reusable eval harness that gates every ZoroLogistics AI artifact.
Day | Task | Status | Notes
Mon | Study evals and error analysis (knowledge-base 07 + Ng's letters). | ☐ Not started
Tue | Define golden eval sets for extraction, RAG, and triage; implement LLM-as-judge with a rubric. | ☐ Not started
Wed | Run the judges; measure judge agreement; calibrate the rubric. | ☐ Not started
Thu | Error analysis: cluster failures from Weeks 6 to 10 artifacts; pick the top fix. | ☐ Not started
Fri | Use case: ZoroEval v1 gates one artifact in a CI-style script; document the loop. | ☐ Not started
Sat | Take the Week 11 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit ZoroEval. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Golden eval sets for extraction, RAG, and triage · LLM-as-judge with a calibrated rubric · ZoroEval harness + CI-style gate script

## Week 12
Week 12, Coding-Agent Harnesses: Claude Code, Cursor, OpenCode, DSH
Section: Harnesses & Loops · Category: Harnesses · ZoroLogistics case study
🎯 Use case: Build the ZoroLogistics ETA CLI (query tool) entirely with a coding agent from a written spec.
Day | Task | Status | Notes
Mon | Install and authenticate 2 harnesses (Claude Code + OpenCode or DSH); read the skill guides. | ☐ Not started
Tue | Write SPEC.md for the ETA CLI: user, constraints, one refused tradeoff, test plan. | ☐ Not started
Wed | Drive the agent to build the CLI; run the tests; iterate until green. | ☐ Not started
Thu | Repeat the same task in a second harness; compare plans, cost, and code quality. | ☐ Not started
Fri | Use case: ship the CLI; write the 1-page harness comparison for your team. | ☐ Not started
Sat | Take the Week 12 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the CLI and comparison. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: ETA CLI built agentically, with tests green · Harness setup + comparison notebook · 1-page harness comparison write-up

## Week 13
Week 13, Agentic Coding Loops & Spec-Driven Development
Section: Harnesses & Loops · Category: Loops & Specs · ZoroLogistics case study
🎯 Use case: Ship the ZoroLogistics Support Bot MVP through the full three-loop cycle with evals closing every loop.
Day | Task | Status | Notes
Mon | Study the three loops and verifier patterns (knowledge-base 01). | ☐ Not started
Tue | Spec the support bot MVP; define the verifier (eval suite + unit tests). | ☐ Not started
Wed | Agentic loop session: build → test → fix until the verifier passes; log the loop. | ☐ Not started
Thu | Developer loop: review with fresh eyes, update the spec, add missed edge cases. | ☐ Not started
Fri | Use case: external loop. Have someone real use the bot; file issues; update spec + evals. | ☐ Not started
Sat | Take the Week 13 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the MVP and loop log. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Support bot MVP with a green verifier (unit tests + eval) · Loop log (agentic/developer/external cycles) · Spec updates driven by feedback

## Week 14
Week 14, Agent Fundamentals: The Loop, Tools & Memory
Section: Agents · Category: Agent Core · ZoroLogistics case study
🎯 Use case: Build the shipment-tracking agent from scratch: lookup, calculator, and web tools.
Day | Task | Status | Notes
Mon | Study the agent loop and ReAct (knowledge-base 10). | ☐ Not started
Tue | Implement the tool-calling loop by hand; wire 2 tools (track shipment, convert units). | ☐ Not started
Wed | Add planning and reflection; log every step: the trace is your debugger. | ☐ Not started
Thu | Add guardrails: refusal, max steps, cost cap; test adversarial inputs. | ☐ Not started
Fri | Use case: the agent solves 10 unseen scenarios; publish the trace log. | ☐ Not started
Sat | Take the Week 14 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the agent and traces. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Hand-written agent with 3+ tools · Trace log of every run · Guardrail tests (refusal, max steps, cost cap)

## Week 15
Week 15, Agent Frameworks: LangGraph & the State-Graph Model
Section: Agents · Category: Frameworks · ZoroLogistics case study
🎯 Use case: Re-implement the support agent in LangGraph with a human approval step for refunds.
Day | Task | Status | Notes
Mon | Study graph-based agent design (knowledge-base 10 + LangGraph docs). | ☐ Not started
Tue | Port the Week 14 agent to LangGraph; visualize the graph. | ☐ Not started
Wed | Add checkpoints and resume; crash mid-run and recover. | ☐ Not started
Thu | Add the human-in-the-loop interrupt for refunds over $500. | ☐ Not started
Fri | Use case: end-to-end run with approval; record latency and tokens per node. | ☐ Not started
Sat | Take the Week 15 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the graph agent. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: LangGraph support agent with visualized graph · Checkpoint/resume demonstration · Human-in-the-loop refund approval flow

## Week 16
Week 16, Multi-Agent Systems & MCP
Section: Agents · Category: Multi-Agent & Protocols · ZoroLogistics case study
🎯 Use case: A support triage team: router + specialists (tracking, refunds, docs) over MCP tools.
Day | Task | Status | Notes
Mon | Study orchestration patterns and MCP (knowledge-base 10/11). | ☐ Not started
Tue | Build an MCP server exposing ZoroLogistics tools; test with an MCP inspector. | ☐ Not started
Wed | Build the multi-agent triage team (supervisor + 3 specialists). | ☐ Not started
Thu | A/B test: multi-agent vs single agent on the same 10 tasks; measure quality and cost. | ☐ Not started
Fri | Use case: publish the A/B report; justify your architecture decision. | ☐ Not started
Sat | Take the Week 16 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the team and the MCP server. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: MCP server exposing ZoroLogistics tools · Multi-agent triage team · A/B report: multi-agent vs single agent

## Week 17
Week 17, OpenClaw, Hermes & Agent Operations
Section: Agents · Category: Personal Agents & Ops · ZoroLogistics case study
🎯 Use case: Deploy a personal ZoroLab assistant (OpenClaw) wired to your MCP server, driven by a Hermes-class model.
Day | Task | Status | Notes
Mon | Study OpenClaw and Hermes (reference/agents/ guides + knowledge-base 10). | ☐ Not started
Tue | Install and configure OpenClaw locally; connect a channel (WebChat or Telegram). | ☐ Not started
Wed | Write 2 OpenClaw skills; wire the Week 16 MCP server; test the context loop. | ☐ Not started
Thu | Swap in a Hermes-class model via Ollama; compare assistant quality. | ☐ Not started
Fri | Use case: add tracing and cost tracking to the assistant; publish the ops runbook. | ☐ Not started
Sat | Take the Week 17 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit skills and the runbook. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Working OpenClaw installation with 2 custom skills · MCP integration with the Week 16 server · Agent ops runbook (tracing + cost)

## Week 18
Week 18, Azure AI Foundry
Section: Cloud AI Platforms · Category: Microsoft · ZoroLogistics case study
🎯 Use case: Deploy the support agent to Foundry with online evaluation and gateway rate limits.
Day | Task | Status | Notes
Mon | Set up the Azure subscription and AI Foundry hub/project (free tier). | ☐ Not started
Tue | Deploy a serverless model endpoint; call it from the Python SDK and OpenAI SDK. | ☐ Not started
Wed | Create the support agent in Foundry with tools; test in the playground. | ☐ Not started
Thu | Run an online evaluation batch; read the trace; fix the worst failure. | ☐ Not started
Fri | Use case: put the agent behind the AI Gateway (rate limit + content safety); publish cost. | ☐ Not started
Sat | Take the Week 18 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the Foundry deployment guide. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Serverless endpoint callable from Python · Foundry agent with tools + evaluation trace · Gateway-governed endpoint with documented cost

## Week 19
Week 19, Google Vertex AI & Gemini
Section: Cloud AI Platforms · Category: Google · ZoroLogistics case study
🎯 Use case: A multimodal bill-of-lading pipeline: Gemini OCR → structured JSON → BigQuery table.
Day | Task | Status | Notes
Mon | Set up Google Cloud and AI Studio; get an API key; check quotas. | ☐ Not started
Tue | Gemini multimodal lab: BoL images → structured JSON; measure accuracy. | ☐ Not started
Wed | Recreate the support agent with ADK/Agent Engine; compare with the Foundry version. | ☐ Not started
Thu | Run a Vertex evaluation on a golden set; log results to BigQuery. | ☐ Not started
Fri | Use case: end-to-end pipeline (images → clean table); publish cost per document. | ☐ Not started
Sat | Take the Week 19 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the Vertex guide. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Multimodal OCR notebook with accuracy measurement · Support agent rebuilt with ADK/Agent Engine · End-to-end pipeline with cost per document

## Week 20
Week 20, AWS Bedrock & SageMaker AI
Section: Cloud AI Platforms · Category: AWS · ZoroLogistics case study
🎯 Use case: A Bedrock RAG support agent with Guardrails, plus the Great Platform Comparison matrix.
Day | Task | Status | Notes
Mon | Set up the AWS account and IAM least-privilege role; enable Bedrock models. | ☐ Not started
Tue | Converse API lab: run the Week 6 prompt suite across Bedrock models. | ☐ Not started
Wed | Build a Knowledge Base (RAG) for shipping policies; query with citations. | ☐ Not started
Thu | Create a Bedrock Agent + Guardrails; test blocked prompts. | ☐ Not started
Fri | Use case: publish the 3-cloud comparison matrix (Foundry vs Vertex vs Bedrock) with cost. | ☐ Not started
Sat | Take the Week 20 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the AWS guide and matrix. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Converse API prompt-suite run across Bedrock models · Knowledge Base RAG with citations · Bedrock Agent + Guardrails; three-cloud comparison matrix

## Week 21
Week 21, Databricks Day Zero: Unity Catalog & the Lakehouse
Section: Databricks Zero to Hero · Category: Platform & Data · ZoroLogistics case study
🎯 Use case: Stand up the ZoroLogistics lakehouse: bronze → silver → gold entirely in SQL.
Day | Task | Status | Notes
Mon | Create the Databricks account/workspace (free trial); tour the UI. | ☐ Not started
Tue | Unity Catalog lab: create catalog/schema/volume; load CSV data; grant rights. | ☐ Not started
Wed | Delta Lake lab: create tables, time travel, VACUUM, OPTIMIZE, liquid clustering. | ☐ Not started
Thu | Medallion in SQL: bronze raw → silver clean → gold aggregates for shipments. | ☐ Not started
Fri | Use case: governed silver/gold tables with lineage; build a first AI/BI dashboard. | ☐ Not started
Sat | Take the Week 21 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the SQL notebooks. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Unity Catalog catalog/schema/volume with grants · Delta tables with time-travel demo · Silver/gold medallion tables + first AI/BI dashboard

## Week 22
Week 22, Databricks Data Engineering: PySpark, Streaming & Lakeflow
Section: Databricks Zero to Hero · Category: Pipelines · ZoroLogistics case study
🎯 Use case: A streaming pipeline: live shipment events → validated silver → on-time KPIs.
Day | Task | Status | Notes
Mon | PySpark lab: transform shipment data with DataFrames; compare with SQL. | ☐ Not started
Tue | Write a DLT pipeline in Python (or SQL) with expectations on data quality. | ☐ Not started
Wed | Add a streaming table for live shipment events (Auto Loader/streaming source). | ☐ Not started
Thu | Create a Lakeflow Job: schedule and orchestrate the pipeline; check runs and lineage. | ☐ Not started
Fri | Use case: the streaming KPI pipeline passes quality gates; publish a monitoring query. | ☐ Not started
Sat | Take the Week 22 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the pipeline code. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: PySpark transformation notebook · DLT pipeline with expectations (data quality gates) · Scheduled Lakeflow Job + monitoring query

## Week 23
Week 23, Databricks ML & GenAI: Training, Serving, Genie
Section: Databricks Zero to Hero · Category: ML & GenAI · ZoroLogistics case study
🎯 Use case: A point-in-time ETA model + RAG over shipping docs + a Genie space for ops analysts.
Day | Task | Status | Notes
Mon | MLflow + feature tables: log a baseline; build point-in-time features. | ☐ Not started
Tue | Train the ETA model (XGBoost or PyTorch); register it in MLflow; compare challenger. | ☐ Not started
Wed | Create the serving endpoint + AI Gateway rate limit; call from Python. | ☐ Not started
Thu | Vector Search: index policy docs; build the RAG chain with ai_query. | ☐ Not started
Fri | Use case: Genie space on the gold tables; verify its SQL; publish it. | ☐ Not started
Sat | Take the Week 23 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker; commit the ML assets. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: Registered ETA model with point-in-time features · Serving endpoint behind the AI Gateway · Vector Search RAG + Genie space with verified answers

## Week 24
Week 24, Databricks Production: DABs, Governance & the Capstone
Section: Databricks Zero to Hero · Category: Production & Capstone · ZoroLogistics case study
🎯 Use case: Capstone: ZoroLogistics Lakehouse Intelligence, deploying the entire Weeks 21 to 23 stack via DABs.
Day | Task | Status | Notes
Mon | Bundle the Weeks 22 to 23 assets into a DAB; validate and deploy with the CLI. | ☐ Not started
Tue | Add CI/CD: GitHub Actions validates and deploys the bundle. | ☐ Not started
Wed | Governance: row filters + column masks + lineage review; write an audit query. | ☐ Not started
Thu | FinOps: billing system-table dashboard; find one cost win; document it. | ☐ Not started
Fri | Use case: capstone demo end-to-end + graduation checklist; publish your portfolio. | ☐ Not started
Sat | Take the Week 24 quiz (quiz.md), pass with 8/10; record the score in Notes. | ☐ Not started
Milestone | Update the Excel tracker: Week 24 done, program complete. | ☐ Not started
Week completion | 0% | ░░░░░░░░░░░░░░░░░░░░ |  | Deliverables: DAB deployable end-to-end (pipeline + model + dashboard) · CI/CD workflow that validates and deploys · Governance + FinOps write-up; graduation checklist

## About
AI Engineering Lab, Progress Tracker
How to use this workbook
1. Fill in your name and start date on the Dashboard sheet.
2. Each week has its own sheet (Week 01 … Week 24) with the week's checklist:
study, notebook, and use-case tasks, one line per program day.
3. Set a task's Status cell (dropdown) to ✅ Done when you finish it. The week's
completion % and the in-cell progress bar update automatically.
4. The Dashboard aggregates every week: status, % bars, phase averages, and a
progress chart. Tick all six tasks in a week to mark it ✅ Complete.
Statuses
☐ Not started · ▶ In progress · ✅ Done · ⏭ Skipped
Skipped tasks count against the week %, use Notes to say why.
Works in: Microsoft Excel, Google Sheets (File → Import), LibreOffice Calc.
The workbook is generated from curriculum/manifest.json by
scripts/build_tracker.py. Edit the manifest, never the xlsx by hand.
© 2026 Zorost Intelligence LLC · https://zorost.com